## Sheet1
Environmental, Social and Governance (ESG) Sustainability Strategy 2035 Targets Action Plan
KPI | Action | Completion Date
Reduce Scope 1 and 2 Carbon Emissions | Manage the Walsall Decarbonisation Project to ensure Decarbonisation of campus in line with Salix requirements. | 24th September 2026
| Work with Transport team to ensure new fleet vehicles are electric or a sustainable alternative. | 31st July 2027
| Embed carbon reduction into the Estates Masterplan phase 2 to drive efficiency and reduce carbon emissions through space rationalisation and campus improvements. | 31st January 2027
| Seek to install energy efficient LED Lighting throughout campuses where budgets permit | On-going as part of LTM
| Review Building Management System to ensure optimisation of carbon saving abilities | 28th February 2027
| Explore innovative technical solutions for decarbonisation including heat networks. | On-going as part of LTM
| Upgrade fixed speed pumps to variable for energy saving | 31st July 2027
| Review gas fired CHP Plant, asessing options for decarbonisation. | 31st March 2027
| Upgrading thermal performance of roof coverings across the campus whilst adding appropriate ventilation for this to breathe. | MN,MD,WS, WN to be complete by August 2026
| Improving insulation to walls and roof voids, where applicable | On-going as part of LTM
| Enhancing air tightness to suit building type to reduce heat loss on existing stock where budgets permit as part of refurbishment programmes | On-going as part of LTM
| Replacing single glazed and failed old double glazing with uprated units where building feasibility and budgets allow. MA a particular focus over the long term. | On-going as part of LTM
| Deploy on-site renewable energy where budgets permit. | On-going as part of LTM
| Ensure that maintenance works adhere to Sustainability requirements as set out in documentation and track the improvements they make to carbon emissions. | On-going as part of LTM
| Seek to apply for funding available for decarbonisation where available | On-going
| Review end of life boilers assessing options for decarbonisation. | On-going
Measure scope 3 emissions and set targets to reduce | Increase depth of scope 3 reporting | 1st February 2027
| Analyse the scope 3 emissions and set targeted actions to reduce | 2027-11-01
Increase Recycling Rates from University student accommodation, teaching and admin buildings. | Waste contractor to complete waste stream audit | Annually
| Create Waste Management Procedure and ensure implementation | 30th November 2026
| Host waste and recycling awareness campaigns to support recycling awareness | Once a year
Sustainable Construction & Refurbishment | Refurbishments and construction projects follow sustainability guidance to include renewables, energy and water conservation measures to benefit projects | On-going
| Green Innovation Corridor - endeavour to embed Sustainability in the programme to refurbish and extend Block A and Block H through sustainable building design and SKA certification | 2026-12-01
| Black Country Medical School - endeavour to embed Sustainability through sustainable building design and exploring potential SKA certification | 2027-09-01
| School of Art - strive to embed that Sustainability through sustainable building design and construction and explore potential certification | 2027-10-01
| Create a furniture Standard Operating Procedure to ensure that furniture is adapted, re-used and recycled to reduce waste. | 2026-12-01
Supporting Biodiversity by increasing vegetation and nature habitats on site | Creation of Wild WLV as a programme to deliver a programme enhancing biodiversity, creating nature habitats and potentially facilitating food growing through staff and student engagement across campuses | 2026-11-01
Sustainable procurement: ESG Inclusion in University tendered contracts | Implement Sustainable Procurement Policy | On-going
| Ensure that ESG questions are included in university tenders | On-going
| Include ESG contributions in the annual Procurement Reports | Annually
Responsible Water Consumption | Work with the Asset Management and Maintenance Team to embed water reduction into maintenance programmes | On-going
| Monitor water usage through loggers to identify opportunities for savings | On-going
Sustainable Catering | Catering to ensure that menu updates include plant based meals in line with targets. | September each year
| Catering to purchase recycled and compostable single use items to support sustainable consumption | On-going
| Catering to promote reusable cups and eating in and booking events with crockery to reduce disposables. | On-going
| To investigate and implement catering carbon emissions monitoring system | 31st August 2026
Sustainable Education | Courses to be re-validated under the new curriculum framework, including sustainability requirements. | 80% by September 2026 and 20% by September 2027
| Creation of 'Living Lab' to study sustainability challenges and opportunities on campus, including for the Walsall Decarbonisation project. | On-going
| Work with the Student Success Team to enahnce the existing SDG Champion Digital Badge for students. Existing SDG Champion badge available for students. Enhanced and expanded provision for students and staff will be made available with opportunities to audit sustainability on-site. | On-going
| Share success stories, case studies and development opportunities for students and staff. | On-going
| Track the numbers of Students engaging in Sustainable Education anually through the completion of the SDG Champion and Sustainability Digital Badge. | Annually from each academic year
Community involvement and university engagement | See Communications and Engagement Action Plan available on the webpages: https://www.wolverhampton.ac.uk/media/departments/estates-and-facilities/documents/Approved_ESG-Communication-and-Engagement-Plan-April-2026.pdf | On-going
| Establish a staff and student sustainability group | 1st February 2027
| Host 3 sustainability events in the academic year | 31st July 2027
Improve the University ranking in the People and Planet League | Complete the Estates Management Return each year including energy, carbon and environment data upon which HESA is scored by the People and Planet League | Annually by April each year
| Update webpages with information and policies that support the People and Planet League methodology. | On-going
| Share People and Planet League Methodology with university stakeholders to guide their policy and webpage updates to support the people and planet league ranking. | On-going
| Investigate Environment Management Systems including ISO and EcoCampus to support People and Planet League Methodology | 31st December 2026
Note that Race Equality Charter and Athena Swan are managed independently by the Equality, Diversity and Inclusion Department who are launching new actions plans during Summer 2026 | *Note that all actions will be subject to governance procedures, budget availability and university Strategic priorities. This action plan will be under constant review.