## Sheet1
HREiR Action plan template July 2021 to July 2023
Details
| Institution name: | The University of Wolverhampton | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 11 | Audience | # | Comments
| Date of submission: | Resubmission 30th July 2021 | Research Only staff | 40
|  |  | Research and Teaching staff | 324 | For those staff with significant responsibility for research.
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Old Concordat principle and clause
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | The Researcher Development Concordat will be published on the Research Web Pages and announced within University of Wolverhampton newsletters. - The Researcher Development Concordat Committee (RCC) will cascade the information within the University. - Information regarding the Research Concordat to be provided to all research staff during the Central Induction programme - including information about the CEDARS questionnaire and the importance of their involvement. - Doctoral College to make the link between the training programmes run for researchers and the Research Concordat obligations at the beginning of each session. - Report to RCC twice per annum on progress with this action plan for further reporting on to the University Research Committee(URC) to extend the reach of the action plan and the understanding of the obligations amongst researchers. | - Publication of the new Concordat and the Researcher Development Concordat signatory letter on the Research web pages. - Achieve a 50% of Research only respondents feeling that they have "some understanding of the Research Concordat" - CEDARS. | Upon completion of the second iteration of CEDARS. | Research Policy Unit (RPU), External Engagement Directorate. Dean of Reasearch & OD team. |  |  | New
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | - All research policies and procedures are to be reviewed periodically as per the policy review schedule and are published on the staff webpages. Policies and procedure updates will be communicated to researchers via Research Matters (newsletter) and discussed at the RCC - In all 'Employee Engagement surveys', produce a separate report showing the views of research staff on key topics (health and wellbeing, policies, practices etc...) to check the extent to which researchers feel they are treated fairly and well in comparison to other job families. - Increase researcher engagement scores and survey completion rates (as measured through the UCEA benchmarking questions which are repeated at 18 monthly intervals). - Annual appraisals will be held to identify researcher development needs using the newly updated 'My DPD' (My Development and Performance Discussion) with bespoke forms for researchers and their managers to use. | - All policies and procedures to be published on website AY 2021/22. - Use of Twitter and other social media to communicate re; policies relevant to researchers - Raise employee engagement survey completion rates from 36% amongst all research staff (Nov 2020) to reach the University average of 47.5% by July 2023. Separate out 'Research only' and 'Teaching and Research' staff to understand completion rates in both groups - Raise the researcher engagement scores (UCEA benchmarking questions) from 59% by 5% to 64% by April 2022) - again separating out 'Research only' and 'Teaching and Research' staff to understand the differences and for action planning purposes. | AY 2021/22 Dec 2021 July 2023 April 2022 | Research Policy Unit (RPU) RPU Deans- measured by Organisational Deveopment (OD) Deans - measured by OD |  |  | P2.1 P6.8
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | - To establish a permanent section regarding the University 'Staff Wellbeing Hub' and the associated core offering around Access to Work Mental Health Support Services, EAP Counselling Service, Togetherall etc... and other wellbeing resources within the 'Research Matters Newsletter'. In this way, keep research staff up to date with new support mechanisms. - To monitor the introduction of the new incident reporting system for trends within incidents reported by research staff. | - To build the numbers of researchers who feel that we have the right levels of wellbeing support in place from 35% (November 2020) to the University average 52% (engagement survey). - Reports to be produced twice per annum on the incident reporting system and incidents reported by researchers (NB - we will have a baseline of the number of incidents reported by July 2021 and will agree an apppropriate reduction). - 50% of researchers to respond positively to the CEDARS questions: "I am familiar with my institution's mechanisms to report bullying and harassment" and "I trust that my institution will investigate any reported incident of bullying and harassment fairly". Investigate any differnences between Research Only staff and Teaching and Research Staff. | April 2022 July 2021 Second iteration of CEDARS questionnaire | OD team Equality, Diversity and Inclusivity Unit (EDI Unit) EDI Unit |  |  | P6.9
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | Increase the awareness of Athena Swan and Race Equality Charter activities and principles. Provide enhanced learning and development for managers of research in inclusivity and diversity (Promotion of the new 'Managing a Respectul Workplace' programme for research managers and mandatory EDI training for all researchers). Review the impact of the revised criteria for the Conferment of Professors and Readers etc... The new process includes an 'Individual Circumstances Panel' to consider any cases where an individual wishes to declare individual circumstances in consideration of their application. The aims of this is to support equality, diversity and wellbeing. Promote the new 'Impactful Leaders' programme and existing 'Inspiring Leaders' programme to researchers to ensure that there is a representative sample of researchers attend the programmes and build the credibility of in house development opportunities. Use attendees to create case studies to promote the programmes to other research staff. Include a health and wellbeing section within each section of Research Matters (newsletter) focusing on the wellbeing support and development tools available for researchers and research managers. | Awareness of Athena Swan increased from 71% of respondents (CROS2019) to 80% in CEDARS 2021 and 85% thereafter. Promotion of new 'Managing a Respectful Workplace' workshops to research managers with a view to ensuring that 50% have completed this training December 2022. Report twice per annum to the RCC on the mandatory E&D training (Equality and Diversity within Higher Education and Unconscious Bias) to show completion rates within researchers. Ensure a completion rate of 90% for both Research Only and Teaching and Research staff by January 2023 and ongoing. Drive the percentage of females applying for conferrment as a Reader, Associate Professor or Professor to 50% (baseline 2020 45%). 7.5% of cohorts for 'Impactful Leaders' and 'Inspiring Leaders' to be researchers. Maintain the currently high scores achieved within the recent Employee Engagement survey (Nov 2020) where 93% of research managers felt very confident / quite confident in discussing staff's mental wellbeing with staff and build those who feel very / quite confident signposting appropriate wellbeing support from 87% to 92%. Investigate any differences between Research Only and Teaching and Research Staff for action planning purposes. | 2021 Dec 2022 January 2023 July 2022 July 2023 Dec 2023 | Athena Swan and REC Self Assessment Team Organisational Development (OD) team, Deans OD Team HR Service, Deans OD Team, Deans OD Team |  |  | P2.3
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | Improve the research environment through Research Centres and Institutes The University's "Handbook for Ethical Review and Approval" is updated annually. At an institutional level, the Ethics Sub-Committee (ESC) deals with policy and procedure and reports to Academic Board through the University Research Committee. (https://www.wlv.ac.uk/media/departments/research/documents/Research-Governance-Committees-2020-21.pdf ) Ensure that all managers of research are aware of the pages on Research Integrity and ethics https://www.wlv.ac.uk/research/research-policies-procedures--guidelines/ Embed research integrity in University researcher development programmes | All Research Centres and Institutes must have defined presence internally and externally by end of 2021 with annual reporting on enhancements. Increased awareness evidenced in CEDARS (baseline 43% CROS2019) - see question 41 - Increase the number of respondents who agree / strongly agree that this institution promotes the highest standards of research integrity and conduct by 5% each iteration to a level of 75%. | 2021 2021 as baseline and 5% increase on each iteration | Directors of Research Institutes and Heads of Centres Doctoral College, Dean of Research, ESC |  |  | P6.1
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | Separate out and understand the voice of the research community within Employee Engagement Surveys (see ECI2) Within recently commissioned work around 'Reflections on Culture' (a culture review), ensure that the voice of researchers is heard by reserving one of the focus groups entirely for researchers and by ensuring that 2 research staff are involved in the 'train to train' work which will allow future iterations of this appreciative inquiry review. | Currently, completion rate for engagement surveys for Research Only staff is 11% (Nov 2020). Work to raise this to 40% within next two years . Bring data from Employee Engagement surveys to the RCC for discussion and action planning following each survey | From next full survey (April 2022) onwards | OD team |  |  | P6.10 P7.5
Funders must:
ECF1 | Including requirements which promote equitable, inclusive and positive research cultures and environments in relevant funding calls, terms and conditions, grant reporting, and policies | [6 empty] | P6.6
ECF2 | Consider how funding opportunities and policies can facilitate different patterns and ways of working, and promote the wellbeing and mental health of researchers | [6 empty] | New
ECF3 | Ensure that funding call requirements and selection processes offer equality of opportunity between different groups of researchers, recognise personal contexts, and promote positive research cultures and working conditions | [6 empty] | P6.6
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | Managers of researchers will need to take part in the learning and development outlined in ECI 4.2. The OD team will measure and report on the percentage of female and BAME staff taking part and report on this to the RCC. The OD team will communicate learning and development opportunities in bespoke communications to research managers so that they can promote training and development. It will also be highlighted to all researchers at both Induction and within Research Matters(newsletter). A new process is currently being built and will be piloted to capture the development undertaken through mentoring and to encourage mentors and mentees to get involved in this highly effective development opportunity. Our aim is that at any one time 20% of researchers within the pilot area have a mentor and that this mentoring activity is recorded. | Managers of researchers to be mindful and supportive of the monitoring of CEDARs Q30 to achieve 5% increase each iteration until 80% reached for the following questions (Q30): - "Your manager / supervisor encourages you to engage in personal and career development opportunities." - "You are aware of the support your Institution provides for your career and professional development." | First iteration of CEDARS establishes base line and ongoing | Managers of researchers (communicated by RCC representatives and through Research Matters) |  |  | New
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | Managers of researchers will need to be part of the work to improve research environments outlined in ECI 5 - specifically, - improving research environments. - ensuring update knowledge regarding research integrity as the Handbook for Ethical Review and Approval is updated year on year. - keeping abreast of the activities of the ESC. | Managers of researchers must support the activities of Research Centres and Institutes to define their presence internally and externally by end of 2021 and the ongoing annual reporting on enhancements. Managers of researchers to be mindful and supportive of the increased awareness targeted in CEDARS (baseline 43% CROS2019) - see question 41. Increase the number of respondents who agree / strongly agree that this institution promotes the highest standards of research integrity and conduct by 5% each iteration to a level of 75%. | end 2021 first iteration of CEDARS as baseline and then ongoing | Managers of researchers (communicated by RCC representatives and through Research Matters) Managers of researchers (communicated by RCC representatives and through Research Matters) |  |  | New
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | Managers of researchers will need to be aware of the actions outlined in ECI 3 regarding the wellbeing resources / tools / development available to them and use the Staff Wellbeing Hub (see link column G) to access tools, information and services to support researchers' wellbeing. The University currently has a Dignity at Work and Study policy and an incident reporting system and work continues to promote this. We have recently submitted our Race Equality Charter to AdvanceHE as part of our REC University Application and in October 2020 we were informed that this application was successful. We are now carrying out our REC action plan. This work will help to promote an effective and safe working environment for all researchers and raise awarness of discrimination. Where appropriate, managers of researchers to attend the 'Let's talk' wellbeing programme (a training programme designed to support managers to have effective wellbeing conversations with their staff built around the HSE 'Talking Toolkit') | Managers of researchers to be supportive of the targeted increases shown below (see ECI3) to: i) build the numbers of researchers who view that we have the right levels of wellbeing support in place from 35% (November 2020) to the University average 52%. ii) ensure that 50% of researchers to respond positively to the CEDARS questions: "I am familiar with my institution's mechanisms to report bullying and harassment" and "I trust that my institution will investigate any reported incident of bullying and harassment fairly". Investigate any differnences between Research Only staff and Teaching and Research Staff. Managers of research to be supportive of the work happening to reduce (ECI 3) i) the number of researchers responding to engagement surveys who have experienced bullying or harassment in the last 12 months from 20% (Nov 2020) to 10% (Dec 2023). ii) the number of researchers who feel unduly stressed at work always or frequently from 51% to the University average (41% as of November 2020 but we hope that this average will also fall) | April 2022 Second iteration of CEDARS questionnaire Dec 2023 April 2022 | Managers of researchers in conjunction with Deans and the OD Team and the Dean of Research Managers of researchers with HR Service Managers of researchers with HR Service Managers of researchers with OD Team | Staff Wellbeing Hub |  | P6.9
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | Managers of researchers will need to take responsibility to keep themselves up to date with institutional policies as they are renewed (ECI2) etc.. through a range of communications - Research Matters (newsletter), ongoing communications from their representatives who sit on the Research Concordat for Development Subcommittee and Faculty information. Managers of researchers to attend all mandatory management training courses (which cover policies etc..) - completion rates will be monitored by the OD Team. - All research policies and procedures are to be reviewed periodically as per the policy review schedule and are published on the staff webpages. Policies and procedure updates will be communicated to managers of researchers via Research Matters (newsletter) and discussed at the RCC for researcher representatives to cascade further. - Managers of researchers to be mindful of and support the drive to increase researcher engagement scores and survey completion rates (as measured through the UCEA benchmarking questions which are repeated at 18 monthly intervals). - Managers of researchers to keep abreast of annual appraisals and the performance development review policy through the refresher training offered annually. | Mandatory management training completion rates increased 5% year on year until reached 85%. - Managers of researchers to be mindful of and support the target increases mentioned in ECI 2, specifically: i) Raise employee engagement survey completion rates from 36% (Nov 2020) to reach the University average of 47.5% by July 2023. Separate out 'Research only' and 'Teaching and Research' staff to understand completion rates in both groups ii) Raise the researcher engagement scores (UCEA benchmarking questions) from 59% by 5% to 64% by April 2022) - again separating out 'Research only' and 'Teaching and Research' staff to understand the differences and for action planning purposes. | AY 2021/22 and ongoing | Managers of researchers with OD Team |  |  | New
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | Managers of researchers will need to play a full part in the actions outlined in relating to improvements in the research environments; continuous updating of research ethics, completion of employee voice activities (eg Employee Engagement Surveys and 'Reflections on Culture' focus groups) - see ECI5 and ECI 6 for fuller details. Aim is to achieve a full focus group (up to 20 researchers - both research only staff and teaching and research staff - encouraged by their line managers) within the 'Reflections on Culture' work. | Managers of researchers to support the activities to enable all Research Centres and Institutes to have a defined presence internally and externally by end of AY 2021/22 with annual reporting on enhancements. Managers of researchers to be mindful and supportive of the targeted increases shown below (reference ECI5 and ECI6) i) Increased awareness evidenced in CEDARS (baseline 43% CROS2019) - see question 41 - Increase the number of respondents who agree / strongly agree that this institution promotes the highest standards of research integrity and conduct by 5% each iteration to a level of 75%. ii)Currently, completion rate for engagement surveys for Research Only staff is 11% (Nov 2020). Work to raise this to 40% within next two years . Bring data from Employee Engagement surveys to the RCC for discussion and action planning following each survey | AY 2021/22 and ongoing First iteration of CEDARS provides baseline and then ongoing. August 2023 | Managers of researchers with Directors of Research Institutes and Heads of Centres Managers of researchers with Doctoral College, Dean of Research, ESC Managers of researchers with OD Team |  |  | New
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | Researchers will need to be aware of and understand the implications for themselves of the activities outlined in ECI 5 and ECI 6 (activities here relate to research integrity and culture work such as the 'Reflections on Culture' activities). This should be demonstrated to their manager, Principal Investigator and discussed during the MyDPD (appraisal). All researchers to take an active part in their MyDPD discussion (appraisal) and agree a "CARE objective" with their line manager. (CARE framework is the new behavioural competency framework all about being Collaborative, Ambitious, Respectful and Effective). All researchers to complete mandatory equality and diversity training. Where appropriate, researchers to take part in mentoring and coaching of other researchers within the University of Wolverhampton and within other HEIs. The reporting on mentoring will be piloted within one Faculty by end of Academic Year 2022 - targets will then be set for other Faculties built around this baseline. | Researchers to support the activities to ensure that all Research Centres and Institutes must have defined presence internally and externally by end of 2021 with annual reporting on enhancements. Researchers to raise any issues regarding research integrity and conduct with the appropriate person (if unsure, their line manager) so that issues can be addressed and the target of acheiving an increased awareness evidenced in CEDARS question 41 - Increase the number of respondents who agree / strongly agree that this institution promotes the highest standards of research integrity and conduct by 5% each iteration to a level of 75%. Researchers to work to complete all mandatory training. Researchers to be mindful and supportive of the monitoring of CEDARs Q30 by getting involved in mentoring / being mentored as appropriate (see EMC1 for further detail) | End of 2021 First iteration of CEDARS as baseline and then ongoing Ongoing First iteration of CEDARS as baseline and then ongoing | Researchers with Directors of Research Institutes and Heads of Centres Researchers and managers of researchers Researchers- monitored by OD Researchers and managers of researchers |  |  | New
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | Researchers will need to be aware of and understand the implications for themselves of the activities outlined in ECI 5.1 regarding research ethics, research environment and cutlure. They will need to be able to draw on this information when working within the University and with Funders. | Researchers to support the aim that all Research Centres and Institutes must have defined presence internally and externally by end of 2021 with annual reporting on enhancements. All researchers to take a responsibility to promote the highest standards of research integrity and to contribute to the CEDARS (baseline 43% CROS2019) - see question 41 - Increase the number of respondents who agree / strongly agree that this institution promotes the highest standards of research integrity and conduct by 5% each iteration to a level of 75%. | End AY 2021 and ongoing First iteration of CEDARS to establish baseline and then ongoing | Researchers with Directors of Research Institutes and Heads of Centres Researchers with Managers of researchers, Doctoral College, Dean of Research, ESC |  |  | P5.3
ECR3 | Take positive action towards maintaining their wellbeing and mental health | Researchers will be encouraged to make full use of the Staff Wellbeing Hub. Links will be further enhanced to recognise those researchers who have contributed to the content of the Hub and thus increase the credibility of these resources amongst researchers. Greater links to be made with University of Wolverhampton health related researchers to understand which elements of their research could be applied for impact on the wellbeing of university staff and their own impact measures. Attend wellbeing training made available from the OD team. Researchers to work with line manager to understand the health and wellbeing support provided and the procedures relating to the reporting of bullying and harassment and provide feedback (both postive and developmental) to allow the institution to improve and hit the CEDARS targets outlined in ECI3 | Measures deadlines and responsibilities are described within ECM 3 and ECI 4 above regarding uptake of EDI and leadership training and health and wellbeing support. Each year, we aim to adopt two key health related research topics and engage with 4 researchers to help them apply the findings of their research within the University. CEDARS question 41 and 25 monitored for a 5% increase each year to 85% on those who agree / strongly agree that "Your institution actively promotes the importance of good mental health and wellbeing of staff" and those who 'You feel confident / fully confident to respond to any issues relating to health and wellbeing.' | See ECM 3 and ECI 4 above AY 2021/22 and ongoing | Researchers with Managers of Researchers supporting OD Team, RPU and Faculty Reps on Research Concordat sub-committee |  |  | New
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | Researchers will need to be aware of the policies and procedures outlined in ECI 3 ( relating to bullying and harassement) and will need to ensure their understanding of the CARE behavioural competency framework outlined in EI5 All research managers will be required to attend the half day briefing on the CARE behavioural competency framework (Collaborative, Ambitious, Respectful and Effective) - they will receive resources to cascade this briefing down to the researchers that they manage. Researchers will need to take an active part within this cascade. | Please see the CEDARS question targets outlined within ECI 3 and EI 5. This will give a clear indication that researchers are able to use the available mechanisms. Managers of research will cascade the information from the 'Manager 'CARE briefing' to the researchers who report to them with the intent that 50% of researchers to respond positively to the CEDARS questions: "I am familiar with my institution's mechanisms to report bullying and harassment" and "I trust that my institution will investigate any reported incident of bullying and harassment fairly" | See ECI 3 and EI5 Second iteration of CEDARS | Researchers with Directors of Research Institutes and Heads of Centres Researchers and managers of researchers. |  |  | P6.9
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | Researchers will need to be involved in the actions outlined in ECI 5 regarding establishing defined internal and external presence for Research Centres. Researchers will be encouraged to get involved in activities such as the 'Reflections on Culture' review; completion of CEDAR and Employee Engagement surveys; collaboration with the HR team on projects such as the CARE framework, career pathways etc... | Measures deadlines and responsibilities are described in ECI 5 and 6 (relate to establishing research centre presence; CEDARS questionnaire regarding integrity; improving the completion rate of Research Only staff from 11% to 40% within employee engagement surveys.) | See ECI5 and ECI6 | Researchers with Directors of Research Institutes and Heads of Centres Researchers with OD team |  |  | P3.13
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | The University already uses anonymous shortlisting and includes a mix of gender and ethnicity within recruitment panels. We are now moving to enhance our use of technology for the recruitment of all research staff. Refreshing of the University applicant attraction strategy across the University with inclusion of attraction of researchers. Develop a programme of work shadowing which supports and facilitates lateral and vertical career moves (eg from Teaching and Scholarly Professional Practice to Teaching and Research role profiles etc...) | Facilitation of multi-device compatible applications; online booking of interview slots; cv parsing and differentiation of application forms (ie so that the application forms completed by researchers are relevant to the roles they are applying for and there are no 'not applicable' sections). Establishment of a senior leadership competency framework linked to pay and reward which will cover senior researchers. Work shadowing scheme in place by August 2023 CEDARS question 17 and 19 raised by 5% annually until a score of 85% and then maintained. "I agree / strongly agree that the promotion pathways and processes at my institution are clear to me" and "I agree / strongly agree that my recruitment, selection and appointment process was fair, inclusive and transparent." | Academic Year 2020/21 and ongoing Academic Year 2020/21 and ongoing August 2023 First iteration of CEDARS used as a baseline and then ongoing | HR Service HR Service HR Service HR Service |  |  | P1.2 P6.2 P6.7
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | The University carried out a major review of induction and launched a new process in January 2019 which has six key criteria, measured through a '30 day new starter quuestionnaire' (measures being 1 - Pre-employment score, 2 Faculty / Directorate support, 3 Availability of resources, 4 Induction training, 5 Induction leadership, 6 HR Support). These measures are reported to the Corporate Management Team (CMT) on an annual basis. The Dean of Research is part of the CMT group. Reference ECM 1- a pilot is being set up within one Faculty to monitor mentoring. As well as aiming for 25% of researchers to have a mentor we will also aim at all new research staff to have a mentor in order to provide support and help with integrating into the relevant research community. It is mandatory that all researchers complete the following courses as part of their induction: - Introduction to Research Supervsion; -Research Supervision and the Research Regulation; -Examing and Chairing Research Degree | Evaluation scores will continue to be reported to CMT on an annual basis. Evaluation scores will be brought to the RCC twice per annum to agree any further actions specific to researchers. This action plan will be monitored by this Committee as a standing agenda item. See measures ECM 1 regarding the CEDARS question target relating to support from line manager and Institution for personal and career development. Report on completion of mandatory induction programmes for researchers will be brought to the Research Concordat Subcommittee twice per annum with a view to ensuring that Q20 CEDARS achieves a 5% increase per annum to 85% finding the induction process local to your current role useful / very useful. | Annually and ongoing Twice per annum AY 2021/22 and ongoing ECM1 Twice per annum AY 2021/22 and ongoing | OD Team OD Team Dean of Research and OD Team OD team provide figures for Doctoral College. |  |  | P3.6
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | Please see EI1 above - Establishment of a senior leadership competency framework linked to pay and reward which will cover senior researchers. Build talent pipelines to support and address any under-representation within the Conferment process for researchers using our clearly laid out 'mitigating circumstances' within this process. For Research Only staff, review what can be provided through appraisal and mentoring processes to support their career / promotion pathways. Report on this to the RCC | CEDARS question 17 and 19 raised by 5% annually until a score of 80% and then maintained. "I agree / strongly agree that the promotion pathways and processes at my institution are clear to me" CEDARS question 14 raised by 5% annually until a score of 80% and then maintained. "I agree / strongly agree that my institution treats me fairly in relation to opportunities for promotion and progression." (Research Only staff) | First iteration of CEDARS as the baseline and then ongoing | Dean of Research and OD Team |  |  | P2.6 P6.3 P6.4 P6.7
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent | Project management development to be offered to all research managers. Project Management workshop for research managers to be designed in collaboration between Project Support staff (Finance Team) and OD team. Offer this to all research managers and monitor uptake. Achieve 25% uptake of Research Only staff by July 2022. Also, encourage managers of research only staff to attend this programme so that full application of learning can be discussed effectively. Promote the new 'Impactful Leaders' programme and 'Inspiring Leaders' programme and the suite of management and personal development workshops and seminars to researchers through the 'Research Matters' newsletter. Use attendees to create case studies to promote the programmes to other research staff. Build three case studies per annum about the application of learning and use these to promote the offering within Research Matters. | Evaluate the management and leadership development delivered to researchers at the following levels: - attendance rates * - satisfaction rates * *(baseline to be established and then targets for growth) Report to go to RCC at the end of each academic year. CEDARS question 14 'To what extent to do you agree that your institution treats you fairly in relation to access to training and development opportunities' to be grown 5% each year to a level of 80% | Jul-2022 Ongoing | OD team OD team |  |  | P2.3
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | Following the launch of the CARE behavioural competency framework (Collaborative, Ambitious, Respectful and Effective) on 1st April 2021, ensure one focus group is dedicated to researchers within the 'Reflections on Culture' project which will commence September 2020 and which will produce heat maps / gap analyses around the extent to which we currently live these behaviours. Produce an action plan, agreed by the RCC, to address any development areas. My DPD (appraisal) completion rates to be monitored for staff on Research Only contracts and Research and Teaching contracts. | CEDARS question 16 - increase 5% year on year until 70% of line managers of research fully / mostly agree that 'Your institution values the contributions you make to appraisal / review of staff' and 'Developing researchers.' | Second iteration of CEDARS and ongoing | OD team and Dean of Research combined with Deans. |  |  | P2.6 P6.3 P6.4
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | As per the review of previous action plan, considerable progress has been made in and we will continue to monitor this and report to the Research Concordat for Development Subcommittee on the findings. A review of current terms and conditions for staff is currently underway, the use of Fixed Term Contracts for researchers will be part of this review. (Jan 2022) | Maintain the improvement in the number of times a Fixed Term Contract is 'rolled over' and the low number of fixed term contracts. | Ongoing | Reports produced annually by HR Service |  |  | P1.3 P2.1 P2.2
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | Research Development Concordat Sub-Committee to review representation from all career stages and to ensure that it is appropriate and that representatives are refreshed on an appropriate time scale. Encourage the take-up of opportunities for Research Only staff to be involved in HR collaborative projects and 'employee voice' activities (surveys, focus groups etc...) HR to identify the research job family as a group for consultation in terms of policy review and development from AY 2021/22 and onwards | CEDARS Q16 - rise in the number of respondents who feel that the institution values the contributions made to institutional policy and decision making. Rise of 5% each iteration to 75% for both Research Only and Teaching and Research staff | Second iteration of CEDARS and ongoing | Dean of Research |  |  | P3.13
Funders must:
EF1 | Include requirements which support the improvement of working conditions for researchers, in relevant funding calls, terms and conditions, grant reporting, and policies | [6 empty] | P2.4
EF2 | Review the impact of relevant funding call requirements on researchers' employment, particularly in relation to career progression and lack of job security | [6 empty] | New
EF3 | Support institutions to develop policies and frameworks to promote sustainable employment arrangements and enhance job security, and provide opportunities for career progression | [6 empty] | P2.4
EF4 | Consider the balance of their relevant funding streams in providing access to research funding and its impact at all career levels | [6 empty] | New
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | Managers of research must review their personal and leadership / management learning and development needs and build a development plan within their MyDPD (appraisal) to meet any gaps and agree this with their line manager. Managers of researchers must complete all mandatory eLearning and management development training Managers of researchers should make themselves aware of new training (for example 'Let's Talk', support for managers to enable them to have wellbeing conversations with their reports and the CARE Framework managers briefing) by reviewing the training available to them in the OD Catalogue and within the Doctoral College 'Staff Researchers Development Programme' available on Canvas at least once per annum ahead of appraisal conversations. Presentation to be built into the Annual Career Development and Research Development Week to update attendees on the range of learning and development available and how it supports the Researcher Development Concordat. | See measures from - ECI4 (measures regarding Leadership, EDI and wellbeing development), - EI 4 (measures regarding management, project management and leadership development) - PDCI1 (measures regarding the provision of opportunities and associated communication to facilitate researchers to be able to attend 10 days of meaningful professional development) - PDCI6 (measures regarding the use of a system, possibly Elements, to record CPD and attendance rates at the Annual Researcher Development Conference). Of note are those measures relating to mentoring, communication of the learning and development offering and individual responsibility of managers of researchers to record their cpd and to encourage researchers to do likewise. | See date provided EC14, EI 4 and PDCI 1 / 6 | See ECI 4, EI 4, PDCI 1/6 |  |  | P2.3
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | HR Policies are available online via our Service Now Portal and web pages. This is signposted at our Central Induction workshop which all researchers and managers of researchers are mandated to attend. The Project Support team within the Finance Dept provide information and support regarding grant funding - managers of researchers are required to use this function to support their work. Guidance for managers of researchers regarding governance is available for managers of researchers on the University governance pages https://www.wlv.ac.uk/about-us/governance/ and within the Research Policies, Procedures and Guidelines web pages https://www.wlv.ac.uk/research/research-policies-procedures--guidelines/ | CEDARS q 41 Your institution promotes the highest standards of research integrity and conduct? Raise this by 5% each iteration until this reaches 80% for research managers See also measures ECI2 and ECI3 noting specifically the importance of communication updates regarding policy. | First iteration of CEDARS and then ongoing See measures ECI1 abd ECI 3 | Managers of Research with the Dean of Research See ECI 1 and ECI 3 |  |  | P2.2
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | Managers of researchers to ensure that all recruitment panels chaired or taken part in have a mix of gender and ethnicity. See also action EI1 and ECI4 particularly focusing on the need of the manager of researchers to be able to used the enhanced technology which will be introduced and to liaise with their HRBP when recruiting to be mindful of updates in legislation / the senior leadership competency framework related to pay etc... | See measures EI1 and ECI 4 particularly focusing on the part that research managers play in achieving the attendance rates in our AdvanceHE "Managing a Respectful Workplace" programme, completion of mandatory training and enhancing scores relating to CEDARS Q19 (See EI 1) | See dates provided EI 1 and EI 4 | See EI 1 and EI 4 |  |  | P6.3
EM4 | Actively engage in regular constructive performance management with their researchers | Managers of researchers will need to take part in activities described EI 5 (please note, the University appraisal process and policy was updated recently and which includes a section specifically for managers of researchers if they do not themselves have significant responsibility for research) Ensure that mandatory appraisal training for managers has been completed and that refreshers are attended. | All Research Centres and Institutes must have defined presence internally and externally by end of 2021 with annual reporting on enhancements. Increased awareness evidenced in CEDARS (baseline 43% CROS2019) - see question 41 - Increase the number of respondents who agree / strongly agree that this institution promotes the highest standards of research integrity and conduct by 5% each iteration to a level of 75%. | See dates provided EI5 | See EI 5 |  |  | P2.3
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | Managers of researchers to encourage researchers to get involved in opportunities described in EI7 and to lead this by example. | Rise in Employee Engagement Survey completion rates by Research Only staff from 11% to 40% (see ECI6) | See dates provided ECI 6 | See ECI 6 |  |  | New
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | Ensure completion of mandatory training which covers many of these areas. Engage with mentor and line manager to develop learning in this area. Use resources within the Researcher Staff Development Programme (Canvas module). Use resources provided by the Research Policy Unit (research data management - https://www.wlv.ac.uk/lib/research/research-data-management/) Attendance at Central Induction and completion of induction checklists with line manager. | Completion rates for mandatory training for researchers reported to Researcher Development Concordat Subcommitee twice per annum. | Starting Academic Year 21/22 and ongoing | OD team and Doctoral College |  |  | New
ER2 | Understand their reporting obligations and responsibilities | Ensure completion of mandatory GDPR and Information Security training Engage with line manager and mentor to understand fully reporting obligations and responsibilities ensuring that agreed actions are completed. | Reporting of completion rates for mandatory training for researchers twice per annum | Starting Academic Year 21/22 and ongoing | OD team |  |  | New
ER3 | Positively engage with performance management discussions and reviews with their managers | Attend all MyDPD and 'Keeping it Live' reviews with line manager, ready to discuss performance, objectives and career aspirations etc… Engage in activities agreed within development plan. Keep CPD log and Researcher Profile (Elements) up to date OD to provide mandatory appraisal training for line managers to ensure effective appraisal provision. | Ensure that 70% of Research Only and Teaching and Research staff feel that MyDPD discussions are effective by December 2023 (although our baseline is unknown the University average is 61% and it is anticipated that this group of staff sit below the average). Monitoring of CPD log and Researcher Profile (Elements) to ensure that these are kept updated | 01/12/2023 Academic Year 2021/22 and ongoing | OD Team Heads of Research Centres / Institutes with line managers |  |  | P5.6
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | Take part in mentor and mentee training / development, management and leadership development as appropriate and required. Contribute to policy and decision making as outlined in EM 5 and EI17 | See measures relating to Employee Engagement Survey completion rates (EM5) and CEDARS Q16 EI 7 | See EM5 | See EM5 |  |  | P5.2
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | It will be mandatory for all new Post Docs to have a mentor in the next academic year. Programme of enhanced support for bid writing to be offered Academic Year 2021/22 Please also above: - ECI4 - leadership and management development programmes - ECM3 - 'Let's Talk' wellbeing training for managers of research - ECR1 - Mandatory E&D training - ECR4 - Briefing on CARE for managers of researchers - EI2 and ER4 - Mentoring - EI4 - Project management - EM1 - Training offered within Organisational Development Training Catalogue and Staff Researchers' Development Programme. Improve communications systems regarding development opportunities using Research Matters, presentations to Research Insitutes and Centres the production of case studies showing the benefits of attending development (see ECI4 and EI4) All research staff to be trained in supervising and examining doctorates. All Teaching and Research Staff and Research Only staff must attend the following: - Introduction to Research Supervsion; -Research Supervision and the Research Regulation; -Examing and Chairing Research Degree In addition, there are 12 further courses on topics such as supporting the wellbeing and additional needs of research students to supporting international students. Explore the functionality of Elements to record CPD activities in 2021. Consult with staff in 2021 and pilot roll-out with system embedded 2022 PCDI 1.4 Implement a system to record the 10 days CPD training required | Monitor the completion of 10 hours of cpd for researchers and report on this annually to the RCC CEDARS question 14 'To what extent to do you agree that your institution treats you fairly in relation to access to training and development opportunities' to be grown 5% each year to a level of 80% - Raise employee engagement completion rates from 36% (Nov 2020) to reach the University average of 47.5% by July 2023. Separate out 'Research only' and 'Teaching and Research' staff to understand completion rates in both groups | September 2021 and ongoing AY 2021/22 and ongoing July 2023 | Directors of Research Institutes and Heads of Centres Project Support Office OD team OD Team Doctoral College / RPU |  |  | P3.1 P3.3 P5.5
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | Monitor the completion rates of MyDPD (My Development and Performance Review) by sampling the appraisal completion rates of 20% of Research Only staff and 10% of Teaching and Research Staff. Hold a focus group with Research Only staff to review the effectiveness of MyDPD in order to establish the use and effectiveness of the new section built in for researchers. Please also see EM4 regarding the mandatory nature of appraisal / MyDPD training for the managers of researchers. | Produce an annual report at the beginning of each academic year commencing 2022 for the RCC showing the sampling, results from the focus group and the completion rates of mandatory appraisal training for the managers of research. CEDARS question 21 - increase the numbers of research only staff and teaching and research staff who required an appraisal and who received an appraisal by 10% at each iteration until reaching 95%. CEDARS question 21a - increase the number of staff who feel their appraisal was useful / very useful by 5% at each iteration until reaching 80% | Sept 2022 and ongoing October 2021 and ongoing See EM4 | OD Team OD Team See EM4 |  |  | P3.10
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | Senior Managers from within the Careers Service attend the Researcher Development Concordat Committee meetings and will produce a plan regarding how the provision of professional advice on career management will be provided by themselves and other colleagues within the University (eg mentors - reference EI 2 and EI 4) The Doctoral College will monitor the uptake of development which supports introductions to funding and research (from search sessions to introducing funding opportunities etc...) and the work achieved within the Lord Paul Fellowship scheme which supports Early Career Researchers to enhance their research leadership skills. Continue to promote and build upon the successful, week long, Annual Research Conference | CEDARS question 30 - increase the number of staff who feel that they are aware of the support their institution provides for their career development on each iteration by 5% building to 80% - Raise the researcher engagement scores (UCEA benchmarking questions) from 59% by 5% to 64% by April 2022) - separating out 'Research only' and 'Teaching and Research' staff to understand the differences and for action planning purposes. | AY2021/22 and ongoing April 2022 | Careers Service OD Team |  |  | P3.1
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | Establish a mentoring system with mentors who have a wide range of experience in different sectors to provide mentoring for all researchers, including ECRs and PGRs, to include internal peer reivew that encourages paper publication and grant applications and improves the quality of papers. See also mentoring actions within EI2 and ER4, work shadowing opportunities within EI1 Launch, promote and monitor uptake of new early career fellowship programme. See PDCI2 re; the Lord Paul Fellowship (LPF) programme: - 4 cohorts of LPFs complete development between 2020 and 2023. Create at least one annual secondment opportunity to the Doctoral College to develop leadership skills Develop action plan based on CEDARS data by end 2021 | Review current university wide mentoring system; All Research Institutes and Centres to establish peer mentoring networks. Launch of LPFs in 2020. 4 cohorts of LPFs complete development between 2020 and 2023. Create at least one annual secondment opportunity to the Doctoral College to develop leadership skills | See EI2 and ER4 End AY 2023 AY 2021/22 | OD team and Directors of Research Doctoral College Dean of Research |  |  | P3.11 P3.14
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | Research Centre and Institutes to review how external partnerships with organisations outside of Higher Education can be and are used to provide enhanced opportunities for researchers. Representatives on the RCC to update on this annually. | CEDARs Q30 monitored to achieve 5% increase each iteration until 80% reached for the following questions (Q30): - "You are aware of the support your Institution provides for your career and professional development." | First Iteration of CEDARS and then ongoing | Directors of Esearch Institutes and Centres and Dean of Research |  |  | P3.2 P3.4
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | All researchers to record professional development activities in Elements. Bi-annual reports on professional development activities provided to Research Institutes / Centres Annual Career Development and Researcher Development weeks. Monitor uptake of activities and attendance to evaluate and improve attendance year on year. | CEDARs Q30 monitored to achieve 5% increase each iteration until 80% reached for the following questions (Q30): - "You are aware of the support your Institution provides for your career and professional development." Report to be provided regarding the number of development activities undertaken by research staff aiming to achieve a consistent level of 10 days minimum. | AY 2021/22 and ongoing | Dean of Research OD Team and Dean of Research |  |  | New
Funders must:
PCDF1 | Incorporate specific professional development requirements in relevant funding calls, terms and conditions, grant reporting, and policies. This should include researchers' engagement in a minimum of 10 days' professional development pro rata per year, and evidence of effective career development planning | [6 empty] | P3.7 P3.9
PCDF2 | Embed the Concordat Principles and researcher development into research assessment strategies and processes | [6 empty] | New
PCDF3 | Acknowledge that a large proportion of the researchers they fund will move on to careers beyond academia, and consider how they can encourage and support this within their remit | [6 empty] | New
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | Please see EI1 above - Establishment of a senior leadership competency framework linked to pay and reward which will cover senior researchers. Knowledge and understanding of this in conjunction with the CARE framework will enable managers of research to understand and discuss career progression in a more effective way. Please see EM1 and EM4 above where managers are expected to be involved in their own appraisals (which includes a section an career development) and attend mandatory training to support them providing effective appraisals for researchers. Please also see PCDI2 above showing the monitoring of competion rates of the mandatory appraisal training for all managers of researchers. | See measures above for EI1, EM1 And EM4, PDCI2 | EI1, EM1, EM4, PDCI2 | EI1, EM1, EM4, PDCI2 |  |  | P2.3
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | Managers of researchers will need to involve themselves in the activities mentioned above - specifically: - ECM1 - the piloting of a mentoring recording system which will identify mentors available, their skills and when mentoring relationships are set up - PDCI 1- ensuring that all new Post Docs who report in to them are allocated a mentor using the system being developed and described in ECM1 - PDCI 3 - ensuring that all researchers reporting to them are encouraged to engage with the activities provided by the Careers Service and are encouraged to take an active part in the Annual Research Development conference - Encourage researchers to join the KEF cafe forum which gives researchers an opportunity to consider the interface between knowledge and exchange and their research impact. - - The KEF cafe is a monthly informal forum for staff involved in or wanting to get involved in knowledge exchange and business engagement activity | See measures above for ECM1, PDCI1 and PDCI3 | ECM1, PDCI1 and PDCI 3 | ECM1, PDCI1 and PDCI 3 |  |  | P3.4 P3.8 P5.5
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | Managers of researchers will draw up professional development plans for this 10 days within the MyDPD (appraisal) development plan for themselves and their direct reports. | See PDCI1 re; the monitoring of the CPD completion rates. See EI4 regarding the evaluation of the management and leadership development delivered to researchers at the following levels: - attendance rates * - satisfaction rates * | PDCI 1 and EI4 | PDCI 1 and EI4 |  |  | New
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | Managers of researchers to engage with HR within projects to support the professional development of researchers such as: - The volunteering scheme which will be established for March 2022 and which will give researchers opportunities to work within organisations in the wider community and network therein. - Build or procurement of a system which will enable research staff to track and drive career development goals for August 2023 | Raise the researcher engagement scores (UCEA benchmarking questions) from 59% by 5% to 64% by April 2022 - again separating out 'Research only' and 'Teaching and Research' staff to understand the differences and for action planning purposes. Number of staff who feel the University has a good reputation raised to 65% by end of academic year 2024 (51% as of November 2020) | April 2022 and ongoing | OD Team with the RCC |  |  | P3.6 P3.9 P5.5
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | Produce a document 'expectations of line managers' by January 2022 which sets out the role and responsivilities of line managers (including managers of researchers). Review this work with managers of research, through their representatives on the RCC, and ensure that they have the right development an operational support (Sept 22). Use the 'expectations of line managers' document to recruit managers of researchers so that they not only have the subject matter expertise but also the foundations of good management and leadership skills and see these as important within their role. | Raise the researcher engagement scores (UCEA benchmarking questions) from 59% by 5% to 64% by April 2022) - again separating out 'Research only' and 'Teaching and Research' staff to understand the differences and for action planning purposes. | April 2022 and ongoing | OD Team with the RCC |  |  | New
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | Researchers to involve themselves in development opportunities as outlined in PDCI1 and mentoring opportunities as described in PDCI4. The uptake of this will be monitored. Researchers to work with their manager to discuss their career development within the MyDPD process and to engage with new initiatives such as the volunteering scheme and system to track / drive career development goals - See PDCM4 Improve communication regarding the above initiatives by using Research Matters (newsletter) and communications from the representatives on the RCC amongst other media | See measures identified in PDCI1, PDCI4 and PDCM4 Ensure communications regarding elements of the HR EiR are included within each Research Matters (newsletter) | PDCI1, PDCI4 and PDCM4 AY 2021/22 and ongoing | PDCI1, PDCI4 and PDCM4 OD Team with Dean of Research |  |  | P5.5
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | Researchers must take advantage of all opportunities within actions PCDI 3, PCDI 4 considering not only research specific development in their chosen research area but also more generic skills (project management, management development, leadership development etc...) which are highly transferable. Researchers to also engage with MyPAL (My Portable Agile Learning), a curated resource library providing researchers with instant online content (videos, articles, checklists, questionnaires etc..) to support their leadership, management and professional development. | See measures identified in PCDI 3 and PDCI 4 and monitoring of researchers using MyPAL to increase this year on year | PCDI 3 and PCDI4 | PDCI3 and PDCI4 |  |  | P3.8
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | MyDPD (appraisal) includes a development plan which encompasses professional development both for a member of staff's current role and for future roles in their chosen career path. Researchers to make full use of the system being built or procured to enable research staff to track and drive career development goals (August 2023) | Discuss, within focus group, the value of the MyDPD development plan and how it can be enhanced. CEDARs Q30 monitored to achieve 5% increase each iteration until 80% reached for the following questions (Q30): - "You are aware of the support your Institution provides for your career and professional development." | AY 2021/22 First iteration of CEDARS provides the baseline and then ongoing | OD Team OD Team and Dean of Research |  |  | P5.5
PCDR4 | Positively engage in career development reviews with their managers | See ER5 above (career development reviews are part of our MyDPD discussion) | Ensure that 70% of Research Only and Teaching and Research staff feel that MyDPD discussions are effective by December 2023 (although our baseline is unknown the University average is 61% and it is anticipated that this group of staff sit below the average). | 2023-12-01 | OD Team |  |  | P3.10
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | Researchers to identify the development opportunities outlined in the following areas which will support this development. ECI 4, EI 4, PCDI 1. Researchers should show that they are involved in a range of development ( from face to face training, mentoring, online learning, volunteering / workshadowing etc..) | See ECI4, EI 4 and PDCI 1 above with associated measures | ECI4, EI 4 and PDCI 1 | ECI4, EI 4 and PDCI 1 |  |  | P5.5
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | To achieve this researchers should work with a mentor who can signpost appropriately as outlined in actions PCDI 4 Researchers to make use of the Development Needs Analysis template which can be found within the Postgraduate Researcher Skills course within Canvas. | CEDARs Q30 monitored to achieve 5% increase each iteration until 80% reached for the following questions (Q30): - "You are aware of the support your Institution provides for your career and professional development." | First iteration of CEDARS provides the baseline and then ongoing | OD Team and Dean of Research |  |  | P5.2
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional suport staff; technicians.